CognitiveSync

TASK/PLAN.md

Version 1.0  |  Unisys Innovation Program Y17

Classification: Confidential

# 1. Plan Overview

This document is the master task and execution plan for CognitiveSync. It defines every task required to go from the current documentation phase to a complete, submission-ready prototype. Tasks are organized by SDLC phase, each with ID, description, effort estimate, dependencies, and status tracking.

| Field | Detail |
| --- | --- |
| Developer | M Santhosh (Solo) |
| Total Estimated Duration | 14 weeks |
| Working Hours Per Day | 3-5 hours (alongside academic commitments) |
| Total Estimated Tasks | 68 tasks across 7 phases |
| Submission Target | Unisys Innovation Program Y17 — final deadline TBC |
| Status Legend | [ ] Not Started [~] In Progress [x] Complete [!] Blocked |

# 2. Master Timeline

| Phase | SDLC Phase | Weeks | Key Milestone |
| --- | --- | --- | --- |
| Phase 1-2 | Formation + Requirements | Week 1 | All 6 documents complete |
| Phase 3 | Design | Week 1-2 | Architecture finalised, repo scaffolded |
| Phase 4A | Construct — Core Pipeline | Week 3-6 | Ingestion + anonymization + feature store working |
| Phase 4B | Construct — Intelligence | Week 7-10 | Graph + GNN + cascade pipeline working end-to-end |
| Phase 4C | Construct — Output Layer | Week 11-12 | Power BI dashboard + Teams bot functional |
| Phase 5 | Test | Week 13 | All tests passing, test summary report complete |
| Phase 6 | Product Release + PPT | Week 14 | Submission-ready — prototype + pitch deck done |

# 3. Phase 1-2 — Formation & Requirements

Phase 1-2 Formation & Requirements ¦ Week 1

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-001 | Draft PRD | 2h | — | [x] |
| T-002 | Draft PID | 2h | T-001 | [x] |
| T-003 | Draft ARCHITECTURE.md | 3h | T-001 | [x] |
| T-004 | Draft TECH_STACK.md | 2h | T-003 | [x] |
| T-005 | Draft WORKFLOWS.md | 3h | T-003 | [x] |
| T-006 | Draft TASK/PLAN.md | 2h | T-001 | [x] |

Phase 1-2 Milestone: All 6 SDLC documents complete and review-ready.

# 4. Phase 3 — Design

Phase 3 Design ¦ Week 1-2

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-007 | Finalise repo directory structure | 1h | T-003 | [ ] |
| T-008 | Scaffold repo — create all dirs and placeholder files | 1h | T-007 | [ ] |
| T-009 | Set up uv project — pyproject.toml, dependencies | 1h | T-008 | [ ] |
| T-010 | Set up pre-commit hooks — ruff + mypy | 1h | T-009 | [ ] |
| T-011 | Set up Docker Compose skeleton — all services defined | 2h | T-008 | [ ] |
| T-012 | Set up PostgreSQL schema — features + scores + audit + config | 2h | T-009 | [ ] |
| T-013 | Design Pydantic v2 schemas for all API request/response models | 2h | T-003 | [ ] |
| T-014 | Design synthetic data generator spec — employee graph, feature vectors | 2h | T-003 | [ ] |
| T-015 | Design GAT model architecture — layer dims, attention heads, hyperparams | 2h | T-004 | [ ] |
| T-016 | Design review — validate all design decisions against PRD requirements | 1h | T-007:T-015 | [ ] |

Phase 3 Milestone: Repo scaffolded, all design decisions locked, ready to code.

# 5. Phase 4A — Construct: Core Pipeline

Phase 4A Construct — Core Pipeline ¦ Week 3-6

## 5.1 Environment & Infrastructure

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-017 | Implement PostgreSQL models with SQLAlchemy 2.x async ORM | 3h | T-012 | [ ] |
| T-018 | Set up Alembic migrations — initial schema | 2h | T-017 | [ ] |
| T-019 | Implement Vault / env-based secrets loader | 2h | T-009 | [ ] |
| T-020 | Implement JWT auth middleware for FastAPI | 3h | T-013 | [ ] |
| T-021 | Implement RBAC middleware — role-based endpoint access control | 3h | T-020 | [ ] |

## 5.2 Synthetic Data Generator

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-022 | Implement synthetic org graph generator — N configurable employees | 3h | T-014 | [ ] |
| T-023 | Implement synthetic feature vector generator — realistic distributions per feature | 3h | T-022 | [ ] |
| T-024 | Implement burnout label generator — rule-based labels from feature thresholds | 2h | T-023 | [ ] |
| T-025 | Implement synthetic edge generator — interaction signals between employees | 2h | T-022 | [ ] |
| T-026 | Validate synthetic data — spot checks, distribution plots | 1h | T-024 | [ ] |

## 5.3 Connector Adapters

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-027 | Implement MS Graph adapter — MSAL auth + calendar/email signal extraction | 4h | T-019 | [ ] |
| T-028 | Implement Slack adapter — slack-sdk async client + message signal extraction | 4h | T-019 | [ ] |
| T-029 | Implement GitHub adapter — PyGithub org client + commit/PR signal extraction | 3h | T-019 | [ ] |
| T-030 | Implement mock adapter — returns synthetic data, used for all testing | 2h | T-023 | [ ] |
| T-031 | Unit test all adapters against mock responses (respx) | 3h | T-027:T-030 | [ ] |

## 5.4 Anonymization Engine

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-032 | Implement PII extractor — identify all identity fields per source | 2h | T-027:T-029 | [ ] |
| T-033 | Implement pseudonymization — SHA-256 + salt UUID v5 generation | 2h | T-019 | [ ] |
| T-034 | Implement encrypted ID mapping store — AES-256-GCM volume write/read | 3h | T-033 | [ ] |
| T-035 | Implement PII discard — verify no identity fields survive anonymization | 2h | T-032:T-034 | [ ] |
| T-036 | Unit test anonymization — verify zero PII in output, deterministic UUID output | 2h | T-035 | [ ] |

## 5.5 Feature Extraction & Scheduler

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-037 | Implement feature extractor — compute all 13 features per pseudo_id per window | 4h | T-035 | [ ] |
| T-038 | Implement normalisation — min-max with rolling org statistics | 2h | T-037 | [ ] |
| T-039 | Implement edge signal extractor — cross-user interaction signals | 2h | T-037 | [ ] |
| T-040 | Implement APScheduler pipeline job — full ingestion chain | 3h | T-037:T-039 | [ ] |
| T-041 | Unit test feature extractor — validate all 13 features compute correctly | 3h | T-038 | [ ] |

Phase 4A Milestone: Full ingestion pipeline operational end-to-end on synthetic data. Feature vectors in PostgreSQL.

# 6. Phase 4B — Construct: Intelligence Engine

Phase 4B Construct — Intelligence Engine ¦ Week 7-10

## 6.1 Graph Builder

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-042 | Implement NetworkX graph builder — node + edge construction from feature store | 3h | T-041 | [ ] |
| T-043 | Implement PyG Data converter — from_networkx with feature matrix + edge tensors | 2h | T-042 | [ ] |
| T-044 | Unit test graph builder — validate node count, edge weights, feature matrix shape | 2h | T-043 | [ ] |

## 6.2 GNN Model

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-045 | Implement GAT model class — 2 GATConv layers + linear output + sigmoid | 3h | T-015 | [ ] |
| T-046 | Implement training pipeline — loss, optimizer, early stopping, mini-batch DataLoader | 4h | T-045 | [ ] |
| T-047 | Train initial model on synthetic graph (100-500 nodes) — RTX 4060 | 3h | T-046 | [ ] |
| T-048 | Evaluate model — accuracy, F1, AUC-ROC on held-out test set | 2h | T-047 | [ ] |
| T-049 | Tune hyperparameters if val_accuracy < 0.80 — lr, heads, hidden dim | 3h | T-048 | [ ] |
| T-050 | Implement model registry — versioned checkpoint save/load | 2h | T-047 | [ ] |
| T-051 | Implement MC Dropout confidence intervals on inference pass | 2h | T-050 | [ ] |
| T-052 | Implement GAT attention weight extraction for feature attribution | 2h | T-051 | [ ] |

## 6.3 Cascade Propagation

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-053 | Implement cascade propagator — 2-hop neighbour traversal with decay | 3h | T-052 | [ ] |
| T-054 | Implement cascade source attribution — tag affected nodes with source list | 2h | T-053 | [ ] |
| T-055 | Unit test cascade — verify propagation math, decay factor, hop limit | 2h | T-054 | [ ] |

## 6.4 FastAPI Intelligence Endpoints

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-056 | Implement /api/v1/scores endpoint — full org scores with RBAC | 2h | T-052 | [ ] |
| T-057 | Implement /api/v1/cascade-map endpoint — full cascade graph response | 2h | T-054 | [ ] |
| T-058 | Implement /api/v1/recommendations endpoint — redistribution logic | 3h | T-056 | [ ] |
| T-059 | Integration test all intelligence endpoints with RBAC enforcement | 3h | T-021, T-056:T-058 | [ ] |

Phase 4B Milestone: Full intelligence pipeline working — graph built, GNN scoring, cascade propagation, all endpoints live.

# 7. Phase 4C — Construct: Output Layer

Phase 4C Construct — Output Layer ¦ Week 11-12

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-060 | Implement Power BI REST API connector — push dataset rows post-scoring | 3h | T-059 | [ ] |
| T-061 | Build Power BI dashboard — heatmap, cascade graph, trend lines, rolling index | 4h | T-060 | [ ] |
| T-062 | Implement Teams bot activity handler — proactive alert messaging | 4h | T-059 | [ ] |
| T-063 | Design HR Adaptive Card — risk summary, signals, recommendations | 2h | T-062 | [ ] |
| T-064 | Design Manager Adaptive Card — redistribution only, zero score exposure | 1h | T-062 | [ ] |
| T-065 | Integration test full pipeline — ingestion to dashboard to bot alert | 4h | T-061, T-064 | [ ] |

Phase 4C Milestone: Full end-to-end demo flow working — data in, scores out, dashboard live, bot firing.

# 8. Phase 5 — Test

Phase 5 Test ¦ Week 13

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-066 | Run full unit test suite — all modules, minimum 80% coverage | 3h | T-065 | [ ] |
| T-067 | Run RBAC penetration tests — verify manager cannot access individual scores via API | 2h | T-066 | [ ] |
| T-068 | Run privacy verification tests — confirm zero PII in all persisted stores | 2h | T-066 | [ ] |
| T-069 | Run end-to-end integration test on clean Docker Compose environment | 3h | T-066 | [ ] |
| T-070 | Performance test — pipeline run time on 500-node synthetic graph | 2h | T-069 | [ ] |
| T-071 | Write test summary report — results, coverage, known issues, risk assessment | 2h | T-070 | [ ] |

Phase 5 Milestone: All tests passing. Test summary report complete. System ready for submission.

# 9. Phase 6 — Product Release & Submission

Phase 6 Product Release + Submission ¦ Week 14

| Task ID | Task | Effort | Depends On | Status |
| --- | --- | --- | --- | --- |
| T-072 | Record demo video — full pipeline walkthrough (3-5 min) | 2h | T-071 | [ ] |
| T-073 | Build UIP pitch deck — problem, solution, architecture, demo, impact, ask | 5h | T-071 | [ ] |
| T-074 | Final review — all documents, code, deck against PRD success criteria | 2h | T-073 | [ ] |
| T-075 | Package submission — documents, deck, repo link, demo video | 1h | T-074 | [ ] |
| T-076 | Submit to Unisys Innovation Program portal | 0.5h | T-075 | [ ] |

Phase 6 Milestone: Submission complete. CognitiveSync delivered to Unisys Innovation Program Y17.

# 10. Total Effort Summary

| Phase | Tasks | Estimated Hours | Calendar Weeks |
| --- | --- | --- | --- |
| Phase 1-2 — Formation & Requirements | 6 | 14h | Week 1 |
| Phase 3 — Design | 10 | 17h | Week 1-2 |
| Phase 4A — Core Pipeline | 25 | 66h | Week 3-6 |
| Phase 4B — Intelligence Engine | 18 | 51h | Week 7-10 |
| Phase 4C — Output Layer | 6 | 18h | Week 11-12 |
| Phase 5 — Test | 6 | 14h | Week 13 |
| Phase 6 — Release & Submission | 5 | 10.5h | Week 14 |
| TOTAL | 76 | ~190h | 14 weeks |

At 3-5 working hours per day alongside academic commitments, 190 hours across 14 weeks is achievable at approximately 2 hours per day average.

# 11. Task-Level Risk Register

| Task(s) | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| T-027:T-029 | Enterprise API access unavailable for real org testing | High | High | All development and demo uses mock adapter (T-030) — real API tested only if credentials available |
| T-047:T-049 | GNN accuracy below 0.80 on synthetic data | Medium | High | Fallback to simpler GCN if GAT fails; tune with Optuna if needed |
| T-046 | OOM on RTX 4060 during training | Medium | Medium | Mini-batch training via PyG DataLoader; reduce hidden dim if needed |
| T-061 | Power BI REST API licensing constraint | Low | Medium | Power BI Desktop sufficient for demo; REST push tested on dev tenant |
| T-062:T-064 | Teams bot proactive messaging setup complexity | Medium | Low | Bot Framework SDK well-documented; fallback to webhook-based alert if needed |
| T-069:T-070 | Docker Compose deployment issues in clean environment | Low | Medium | Test on fresh VM early in Phase 5; document all env var requirements |
| T-073 | PPT preparation time pressure after 14 weeks of solo build | Medium | Medium | Deck structure planned now; content reused from SDLC documents |

# 12. Definition of Done

A task is complete when all of the following are true:

- Implementation matches the specification in ARCHITECTURE.md or WORKFLOWS.md

- Unit tests written and passing for all non-trivial logic

- ruff linting passes with zero errors

- mypy type checking passes with zero errors

- Code reviewed by self against checklist (logic, edge cases, error handling, logging)

- Relevant documentation updated if design decision changed during implementation

A phase is complete when:

- All tasks in the phase reach Done status

- Phase milestone is verified against PRD success criteria

- All tests relevant to the phase are passing

- No open Blocked tasks remain unresolved

# Document Control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 2026-03-21 | M Santhosh | Initial draft — Unisys Innovation Program Y17 submission |